# PACK 2 — HET AI, Cyber & Digital Skills Portfolio

Portfolio Plan & Operating Model (Version 1)

Owner: Heartfulness Education Trust (HET)

Delivery Model: Online-first, PAN-India (Hybrid only for select longer programs)

Time Horizon: Year 1 (12 months) execution plan

Scale Target: 60,000+ NCVET-ready trainings with assessment & certification

# 1. Purpose of Pack 2

Pack 2 translates the strategic intent defined in Pack 1 into an executable operating model. It defines how the HET AI, Cyber & Digital Skills Portfolio will be delivered at national scale, primarily through online modes, while ensuring NCVET readiness, assessment integrity, and quality outcomes.

# 2. Year-1 Operating Assumptions

## 2.1 Delivery Assumptions

- Primary delivery mode: Online (self-paced + live instructor-led sessions)

- Hybrid delivery limited to selected 60-hour and 90-hour programs

- PAN-India delivery through the Heartfulness network of centers

## 2.2 Scale & Volume Assumptions

- Total Year-1 certifications target: 60,000+

- Tier 1 (Micro-credentials): 60–70% of volume

- Tier 2 (60-hour upskilling): 20–30% of volume

- Tier 3 (90-hour job-linked): 5–10% of volume

## 2.3 Certification & Credit Assumptions

- Micro-credential certificate issued per course

- Minimum course duration: 7.5–8 hours (0.25 credits)

- Credit alignment as per National Credit Framework (NCrF)

# 3. Phased Rollout Plan (12 Months)

## Phase 1: Foundation & Pilot (Months 1–3)

Objectives: Lock standards, pilot delivery, validate assessment systems

Key Activities:

- Finalize course dossier and assessment templates

- Pilot 5 flagship courses (AI-101, DIG-101, CYS-101, AI-201, CYS-401)

- Train master trainers and assessors

- Launch controlled online cohorts

Expected Output: 3,000–5,000 certified learners

## Phase 2: PAN-India Scale-Up (Months 4–9)

Objectives: Rapid scale of micro-credentials and domain programs

Key Activities:

- National rollout of AI-1xx, CYS-1xx, DIG-1xx courses

- Expansion of AI-2xx and CYS-2xx programs

- CSR and institutional cohort onboarding

Expected Output: 40,000–45,000 cumulative certifications

## Phase 3: Consolidation & Outcomes (Months 10–12)

Objectives: Strengthen outcomes and prepare Year-2 roadmap

Key Activities:

- Scale 60-hour and 90-hour employability programs

- Strengthen placement and livelihood tracking

- Produce Year-1 impact and readiness reports

Expected Output: 60,000+ certified learners

# 4. Delivery Architecture (Online-First)

Centralized HET Functions:

- Curriculum and content repository

- Assessment bank and certification engine

- Trainer and assessor accreditation

- MIS, reporting, and quality assurance

Decentralized Heartfulness Network Functions:

- Learner mobilization and onboarding

- Cohort coordination and facilitation

- Local support and assessment facilitation where required

# 5. Trainer & Assessor Operating Model

Trainer Structure:

- Master Trainers: Content ownership and pedagogy

- Program Trainers: Course delivery

- Facilitators: Learner support

Assessor Structure:

- Centralized assessor pool certified by HET

- Independence between trainers and assessors

- Standard rubrics and moderation protocols

# 6. Assessment, Certification & Credit Operations

All courses follow a uniform Explain–Evaluate–Execute assessment principle:

- Explain: Knowledge checks (MCQs)

- Evaluate: Scenario-based judgment

- Execute: Practical tasks or artifacts

Certification Flow:

- Course completion

- Summative assessment

- Result processing

- Certificate issuance

# 7. Monitoring, Evaluation & Reporting

- Operational KPIs: enrollment, attendance, assessments, certifications

- Outcome KPIs: employability, productivity uplift, learner progression

- Reporting cadence: monthly dashboards, quarterly reports, annual impact summary

# 8. Risk Management & Mitigation

- Quality dilution mitigated through standardized templates and moderation

- Trainer scarcity mitigated via train-the-trainer pipelines

- Assessment integrity ensured through scenario and artifact-based evaluation

- Cash-flow risk managed by separating reach programs from outcome-linked programs